# Resource Plan

Enrollment & Claims Platform Modernization

The 20-person named-leads roster for this program — the same set of people the Program Budget's rate card reconciles to exactly.

## Named-Leads Roster (20)

| Resource | Role | Location | Allocation | Blended Rate | Est. Hours | Est. Labor Cost |
| --- | --- | --- | --- | --- | --- | --- |
| C. Tyrrell | Program Manager | Onshore (US) | Full-Time | $175/hr | 2,383 | $417,025 |
| F. Jones | Lead Business Analyst | Onshore (US) | Full-Time | $140/hr | 1,120 | $156,800 |
| J. Albert | Solution Architect | Onshore (US) | Full-Time | $165/hr | 1,600 | $264,000 |
| M. Alvarez | System Upgrade Lead / Platform Engineer | Onshore (US) | Full-Time | $155/hr | 835 | $129,425 |
| T. McCormick | Data Conversion Lead | Onshore (US) | Full-Time | $150/hr | 1,360 | $204,000 |
| R. Whitfield | QA / Test Lead (Onshore) | Onshore (US) | Full-Time | $125/hr | 1,800 | $225,000 |
| P. Sundaram | Offshore QA Coordination Lead | Offshore | Full-Time | $65/hr | 1,400 | $91,000 |
| D. Okafor | Developer - Billing Integration | Onshore (US) | Full-Time | $130/hr | 1,200 | $156,000 |
| S. Lindqvist | Developer - Underwriting Integration | Onshore (US) | Full-Time | $130/hr | 1,200 | $156,000 |
| K. Delgado | Developer - Claims Administration Integration | Onshore (US) | Full-Time | $130/hr | 1,200 | $156,000 |
| P. Novak | Developer - Commission Management Integration | Onshore (US) | Full-Time | $130/hr | 1,104 | $143,520 |
| A. Reyes | Developer - Data Warehouse/Reporting Integration | Onshore (US) | Full-Time | $130/hr | 1,104 | $143,520 |
| B. Sato | Developer - Payment Processing Integration | Onshore (US) | Full-Time | $130/hr | 1,104 | $143,520 |
| L. Bergstrom | Change Manager (OCM Lead) | Onshore (US) | Full-Time | $145/hr | 1,536 | $222,720 |
| H. Osei | Training Lead | Onshore (US) | Full-Time | $110/hr | 1,210 | $133,056 |
| V. Alaoui | Customer Experience Manager | Onshore (US) | Part-Time | $120/hr | 320 | $38,400 |
| N. Sharma | Compliance / Legal Representative | Onshore (US) | Part-Time | $180/hr | 624 | $112,320 |
| G. Fenwick | Internal Audit / SOX Compliance Lead | Onshore (US) | Part-Time | $150/hr | 480 | $72,000 |
| W. Donnelly | Vendor / Procurement Manager | Onshore (US) | Part-Time | $145/hr | 600 | $87,000 |
| E. Kowalski | PMO / Governance Analyst | Onshore (US) | Part-Time | $135/hr | 520 | $70,200 |
| TOTAL (Named Leads Only) |  |  |  |  |  | $3,121,572 |

## Reconciliation to Program Budget

| Source | Total |
| --- | --- |
| Resource Plan (this page) | $3,121,572 |
| Program Budget - Resource Rate Card (Named Leads) | $3,121,572 |
| Variance | $0 |

This document and the Program Budget's rate card are the same 20-person dataset by design. Category-level Budget totals (which additionally include unnamed team members) are a separate, larger figure — see the Program Budget for that view.

## Reporting Structure & Notes

Full reporting-line diagram is maintained in the Org Chart — this document intentionally doesn't duplicate that structure, only the staffing/cost view of the same roster.

P. Sundaram is the program's only offshore resource, coordinating the offshore QA function under R. Whitfield's onshore QA/Test Lead role.

Part-Time allocations (Alaoui, Sharma, Fenwick, Donnelly, Kowalski) reflect oversight/governance functions that don't require full-time engagement across the program's full duration.

Staffing changes exceeding the Program Manager's standing authority follow the escalation path in the Program Governance Model.

Illustrative program data — created to demonstrate PMBOK/waterfall program management practice, not a real client engagement.