Enrollment & Claims Platform Modernization

Weekly Status Report — Portfolio Demo

Program Manager: C. Tyrrell     |     Report No.: WK-24     |     Reporting Period: 11-17 Jan 2027     |     Distribution: Steering Committee

# Executive Summary

Enrollment & Claims Platform Modernization is in Phases 3 & 4 (Data Conversion / Integration Build entry) and is currently in Yellow status due to a high-severity data quality risk (R-001) in the historical claims data. The get-to-Green strategy is to complete early data profiling and automated cleansing rules ahead of Dry Run 2, escalate any systemic issues to the Business Data Owner immediately, and hold a third Dry Run in reserve if reconciliation tolerance isn't met. No change to the Data Conversion Sign-off milestone (16 Mar 2027) is being proposed this period.

## Status Summary

| Metric | Status |
| --- | --- |
| Overall Status | Yellow |
| Schedule | 42% Complete |
| Budget | 43% Spent |
| Open Risks (High) | 1 |

## Accomplished — Week of 11-17 Jan 2027

- Staging TLS configuration remediated  —  External penetration test finding (I-005) patched and re-scanned clean. Owner: M. Alvarez

- System Upgrade Validated milestone achieved (05 Jan 27)  —  Phase 2 formally closed. Owner: M. Alvarez

- Data Conversion and Integration Build phases entered  —  Phase 3 and Phase 4 both opened. Owner: T. McCormick / C. Tyrrell

- Architecture decision log established  —  For Solution Architect cross-training continuity (A-004). Owner: J. Albert

## Planned — Week of 18 Jan 2027

- Begin Data Conversion mapping  —  Member/policy data mapping kickoff (WBS 3.1). Owner: T. McCormick

- Begin Integration Build Sprint 1  —  Across all six integration tracks. Owners: D. Okafor / S. Lindqvist / K. Delgado / P. Novak / A. Reyes / B. Sato

- Finalize offshore/onshore QA handoff protocol (A-001)  —  Awaiting onshore Test Lead sign-off. Owner: P. Sundaram / R. Whitfield

- Monitor vendor SOW negotiation (DEP-003, At Risk)  —  Ahead of Environment Provisioning start. Owner: W. Donnelly

## Risks & Issues Requiring Attention

| ID | Description | Owner | Status / Action |
| --- | --- | --- | --- |
| R-001 | Historical claims data quality issues (Score 9, High/High) | T. McCormick | Early profiling underway; cleansing rules being drafted ahead of Dry Run 2 |
| R-003 | Vendor SOW negotiation delay (Score 6, Medium/High) | W. Donnelly | Backup vendor pre-qualified as contingency (A-003, Complete) |
| I-003 | Vendor demo missed integration middleware requirement | W. Donnelly | Supplemental technical session held; vendor response pending |
| DEP-003 | Platform vendor SOW must finalize before Environment Provisioning | W. Donnelly | Status: At Risk — contract negotiation in progress |

## Budget Health & Variance

Budget Status: On Track

| Metric | Value |
| --- | --- |
| Current Period Variance | +$45K (+0.6%) |
| Projected Variance at Completion | +$148K (+2.1%), EAC vs. BAC |
| Spent to Date | $3.05M |
| Forecast at Completion | $7.21M |
| Contingency Remaining | $0.58M of $0.642M |

Contingency is currently held in reserve against R-001 (historical claims data quality) in case a third Data Conversion Dry Run cycle is required. No baseline re-plan is recommended at this time.

## Upcoming Milestones

| Milestone | Date | Status |
| --- | --- | --- |
| Project Kickoff | 04 Aug 26 | Complete |
| Requirements & Vendor Selection Complete | 03 Nov 26 | Complete |
| System Upgrade Validated | 05 Jan 27 | Complete |
| Data Conversion / Integration Build (current) | In progress | Current |
| Data Conversion Sign-off | 16 Mar 27 | Upcoming |
| Integration Build Complete | 11 May 27 | Upcoming |
| Testing Complete / UAT Sign-off | 10 Aug 27 | Upcoming |
| Go-Live (Production Cutover) | 24 Aug 27 | Upcoming |
| Production Support Handover / Closeout | 02 Nov 27 | Upcoming |

Illustrative program data — built to demonstrate PM tooling and reporting design, not a real client engagement.