## Slide 1
ACME COMPANY
Enrollment & Claims
Platform Modernization
Monthly Program Update — Steering Committee
15 January 2027
Presented by C. Tyrrell, Program Manager

## Slide 2
AGENDA
What We'll Cover Today
Executive Summary
Overall program health and key message
Decision Requested
One item for Steering Committee approval
Schedule & Milestones
Phase progress and the road ahead
Budget & Financials
Spend, forecast, and variance
Risks, Issues & Quality
What's on watch and how we're tracking
Resources & Change Control
Team status and governance activity
Enrollment & Claims Platform Modernization · ACME Company · Illustrative Portfolio Demonstration
2

## Slide 3
EXECUTIVE SUMMARY
Program Health at a Glance
YELLOW
Data Conversion & Integration Build phases now underway.
Program has completed Initiation, Requirements & Vendor Selection, and System Upgrade Validation. A high-severity data quality risk in the historical claims data (R-001) could extend the Data Conversion timeline if root-cause cleansing proves insufficient. Get-to-Green plan: complete data profiling ahead of schedule and hold a third Dry Run cycle in reserve. No milestone changes are being proposed this period.
37%
SCHEDULE COMPLETE
43%
BUDGET SPENT
+2.1%
FORECAST VARIANCE
1
HIGH-SEVERITY RISK
Next Milestone: Data Conversion Sign-off — 16 March 2027
Enrollment & Claims Platform Modernization · ACME Company · Illustrative Portfolio Demonstration
3

## Slide 4
DECISION REQUESTED
Pre-approve contingency utilization of up to $150,000 for a third Data Conversion Dry Run cycle, should root-cause cleansing of historical claims data (R-001) prove insufficient ahead of the scheduled Dry Run 2.
WHY THIS MATTERS
Protects the Data Conversion Sign-off milestone (16 Mar 2027)
Contingency Reserve currently has $0.58M of $0.642M available — sufficient capacity
No schedule impact if approved and invoked promptly; avoided cost if not needed
RECOMMENDATION: Approve
Enrollment & Claims Platform Modernization · ACME Company · Illustrative Portfolio Demonstration
4

## Slide 5
SCHEDULE
Program Timeline & Milestones
Project
Kickoff
04 Aug 26
Requirements &
Vendor Selection
03 Nov 26
System Upgrade
Validated
05 Jan 27
Data Conversion
Sign-off
16 Mar 27
Integration Build
Complete
11 May 27
Testing / UAT
Sign-off
10 Aug 27
Go-Live
24 Aug 27
Where We Are
The program has passed three consecutive gate milestones on schedule. Data Conversion and Integration Build are now running in parallel — the program's most execution-intensive stretch — with Testing entrance criteria being prepared alongside. The next gate, Data Conversion Sign-off, is 60 calendar days out.
Enrollment & Claims Platform Modernization · ACME Company · Illustrative Portfolio Demonstration
5

## Slide 6
SCHEDULE
Progress by Phase
Chart: 
| 1. Initiation & Requirements | 2. System Upgrade | 3. Data Conversion | 4. Integration Build (Agile) | 5. Testing (Functional-UAT) | 6. Cutover & Hypercare | 7. Change Mgmt & Training | 8. Program Governance & Risk
% Complete | 100 | 100 | 16 | 9 | 5 | 0 | 37 | 42
KEY TAKEAWAY
Phases 1 & 2 are fully closed. Phases 3 & 4 have just opened and will ramp quickly over the coming weeks. Change Management and Governance run continuously in parallel across the whole program.
37%
OVERALL SCHEDULE COMPLETE
Enrollment & Claims Platform Modernization · ACME Company · Illustrative Portfolio Demonstration
6

## Slide 7
PROGRESS
Key Accomplishments This Period
Staging security finding remediated
External penetration test flagged an outdated TLS configuration; patched and re-scanned clean.
M. Alvarez
System Upgrade Validated milestone achieved
Phase 2 formally closed on schedule (05 Jan 2027), clearing the path for Conversion and Build.
M. Alvarez
Data Conversion & Integration Build phases opened
Both workstreams entered execution in parallel this period.
T. McCormick / C. Tyrrell
Architecture continuity established
Decision log created to cross-train the Business Analyst on architecture rationale.
J. Albert
Enrollment & Claims Platform Modernization · ACME Company · Illustrative Portfolio Demonstration
7

## Slide 8
LOOK AHEAD
Planned for Next Period
Begin Data Conversion mapping
Member/policy data mapping kickoff
T. McCormick
Begin Integration Build Sprint 1
Across all six integration tracks
6 Track Developers
Finalize offshore/onshore QA handoff
Awaiting onshore Test Lead sign-off
P. Sundaram / R. Whitfield
Monitor vendor SOW negotiation
Status: At Risk — contract in progress
W. Donnelly
Next Steering Committee gate: Data Conversion Sign-off review — 16 March 2027
Enrollment & Claims Platform Modernization · ACME Company · Illustrative Portfolio Demonstration
8

## Slide 9
FINANCIALS
Budget & Financial Status
Chart: 
| Platform Upgrade | Integration Middleware | Internal Labor | QA Labor | Development Labor | Infra- structure | Training & Change Mgmt | Contin- gency
Budget ($K) | 1850 | 620 | 1240 | 780 | 1340 | 410 | 180 | 642
$7.062M
TOTAL BUDGET
$3.05M
Spent to Date (43%)
$7.21M
Forecast at Completion
+2.1%
Variance to Baseline
$0.58M
Contingency Remaining
Full variance is attributed to Internal Labor, reflecting Data Conversion Lead time held in reserve against R-001.
Enrollment & Claims Platform Modernization · ACME Company · Illustrative Portfolio Demonstration
9

## Slide 10
RISKS & ISSUES
Top Risks Requiring Attention
R-001
Historical claims data quality issues
Early profiling & automated cleansing rules underway ahead of Dry Run 2
Score 9 · High/High
Owner: T. McCormick
R-003
Vendor SOW negotiation delay
Backup vendor pre-qualified as contingency
Score 6 · Medium/High
Owner: W. Donnelly
R-002
Offshore/onshore QA coordination gaps
Daily overlap-hour standup in place
Score 4 · Medium/Medium
Owner: R. Whitfield
DEP-003
Platform vendor SOW must finalize before Environment Provisioning
Contract negotiation in progress
At Risk
Owner: W. Donnelly
Enrollment & Claims Platform Modernization · ACME Company · Illustrative Portfolio Demonstration
10

## Slide 11
QUALITY
Quality & KPI Dashboard
Metric | Target | Current Status
Schedule Performance Index (SPI) | ≥ 0.95 | On Track
Cost Performance Index (CPI) | ≥ 0.95 | On Track
Data Conversion Accuracy | ≥ 99.5% record match | Not Yet Measurable — Dry Run 1 Pending
Critical/High Defect Escape Rate to UAT | ≤ 5% | Not Yet Measurable — Build In Progress
Security Findings (Critical/High) at Go-Live | 0 | On Track — Staging Finding Remediated
Training Completion Rate | ≥ 95% prior to Go-Live | Not Started — Scheduled Later Phases
Hypercare Severity-1 Incidents | ≤ 2 | Not Yet Applicable
Enrollment & Claims Platform Modernization · ACME Company · Illustrative Portfolio Demonstration
11

## Slide 12
TEAM
Resource & Team Status
Chart: 
| C. Tyrrell (PM) | J. Albert (Architect) | T. McCormick (Data Conv.) | M. Alvarez (Sys. Upgrade) | R. Whitfield (QA-Onshore) | P. Sundaram (QA-Offshore) | 6 Integration Developers
Utilization % | 100 | 90 | 100 | 70 | 65 | 50 | 80
Program team stands at 20 named resources across Program Management, Architecture, Data Conversion, System Upgrade, QA (onshore/offshore), six Integration Development tracks, Compliance/Audit, Procurement, Governance, Change Management, Training, and Customer Experience.
Enrollment & Claims Platform Modernization · ACME Company · Illustrative Portfolio Demonstration
12

## Slide 13
GOVERNANCE
Change Control Summary
10 / 10
CHANGE REQUESTS
IMPLEMENTED
Security, Performance & DR Testing added
Steering Committee approved — Testing phase scope
SOX Control Impact Assessment & Compliance Testing
Steering Committee approved — updated WBS, PM Plan, RAIDD Log, Resource Register
Offshore QA Coordination role & dual-shore model
PM-approved — added capacity ahead of Build ramp-up
All change requests to date have followed the program's tiered governance model (PM / PMO / Steering Committee) and are fully reflected in the WBS, PM Plan, RAIDD Log, and Resource Register.
Enrollment & Claims Platform Modernization · ACME Company · Illustrative Portfolio Demonstration
13

## Slide 14
APPENDIX
Steering Committee Roster
Name | Role | Voting
G. Whitfield | Executive Sponsor (VP of Operations) | Yes
A. Marchetti | CIO / VP of Information Technology | Yes
R. Castellano | VP, Underwriting | Yes
J. Boudreaux | VP, Claims Administration | Yes
S. Whitcombe | VP, Finance | Yes
N. Sharma | Chief Compliance Officer / General Counsel | Yes
S. Ryan | Director, PMO | Yes
C. Tyrrell | Program Manager (briefs the committee) | No
Enrollment & Claims Platform Modernization · ACME Company · Illustrative Portfolio Demonstration
14

## Slide 15
Questions & Discussion
C. Tyrrell, Program Manager
Enrollment & Claims Platform Modernization · ACME Company